## Inventory
System Name: Inventory Management
Members:
Marck Ramon G. Paraiso
Andrei Mighel A. Gabison
William P. Bustamante
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September | [30 empty] | October | [30 empty] | November | [30 empty] | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1. User Authentication and Access Control | Paraiso | 2024-09-06 | 2024-09-08 | Done | bar: September 5 to September 8
1.1. Creating UI for Login/Sign-up | Paraiso | 2024-09-06 | 2024-09-08 | Done | bar: September 5 to September 8
1.2. Integrating UI with Database for Authentication | Paraiso | 2024-09-06 | 2024-09-08 | Done | bar: September 5 to September 8
2. Product Catalog Management | Paraiso & Bustamante & Gabison | 2024-09-20 | 2024-09-22 | Done | bar: September 19 to September 22
2.1. Creating UI for Adding/Editing items | Gabison | 2024-09-20 | 2024-09-22 | Done | bar: September 19 to September 22
2.2. Integrating with Database | Paraiso & Bustamante & Gabison | 2024-09-20 | 2024-09-22 | Done | bar: September 19 to September 22
2.4. Product adding, deletion, and modification | Paraiso | 2024-10-04 | 2024-10-06 | Done | bar: October 3 to October 6
3. Stock Level Tracking | Bustamate | 2024-10-04 | 2024-10-06 | Done | bar: October 3 to October 6
3.1. Creating UI for Stock Monitoring | Bustamate | 2024-10-04 | 2024-10-06 | Done | bar: October 3 to October 6
3.2. Database Integration for Stock Updates | Paraiso & Bustamante & Gabison | 2024-10-04 | 2024-10-06 | Done | bar: October 3 to October 6
3.3. Low Stock Alert System w/ notification | Gabison | 2024-11-16 | 2024-11-22 | Done | bar: November 15 to November 22
3.4. Real-time Stock Information | Gabison & Bustamante | 2024-11-16 | 2024-11-22
4. Manual Order Management | Paraiso | 2024-10-25 | 2024-10-27 | Done | bar: October 24 to October 27
4.1. Creating UI for Adding/Editing Orders | Paraiso | 2024-10-25 | 2024-10-27 | Done | bar: October 24 to October 27
4.2. Database Integration for Manual Order Entry | Paraiso | 2024-10-25 | 2024-10-27 | Done | bar: October 24 to October 27
4.3. Order Confirmation/Tracking(adds arrived order to inventory) | Gabison | 2024-11-19 | 2024-11-20 | Done | bar: November 19 to November 22
4.4. Order History and Overview Implementation | Paraiso | 2024-10-25 | 2024-10-27 | Done | bar: October 27
5. Search Functionality | Paraiso & Gabison | 2024-10-22 | 2024-10-27 | Done | bar: October 22 to October 27
5.1. Creating Search UI for Products/Orders | Gabison | 2024-10-22 | 2024-10-22 | Done | bar: October 22 to October 27
5.2. Implementing Search Algorithm | Gabison | 2024-10-22 | 2024-10-27 | Done | bar: October 22 to October 27
5.3. Adding Filters (By Category) | Gabison | 2024-10-24 | 2024-10-26 | Done | bar: October 23 to October 26
6. Export Data | Bustamate | 2024-10-24 | 2024-10-26 | Done | bar: October 23 to October 26
6.1. Creating a simple UI for Export | Bustamate | 2024-10-24 | 2024-10-26 | Done | bar: October 23 to October 26
6.2. Implementing CSV Export ( Basic Python csv library ) | Bustamate | 2024-10-24 | 2024-10-26 | Done | bar: October 23 to October 26

## Setup
Members
Paraiso
Gabison
Bustamate
Paraiso & Gabison
Paraiso & Bustamante
Gabison & Bustamante
Paraiso & Bustamante & Gabison